## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | A.M; 03/19/2025
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | A.M; 03/19/2025
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Pass | A.M.; 03/19/2025
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | A.M.; 03/19/2025
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | A.M.; 03/19/2025
As a U-fund Manager, I should not have access to the contents of funding baskets so that funding privacy is maintained. | Given I am logged in as a U-fund Manager, when I navigate the system, then I do not see any Helper's funding basket. | Pass | E.L.; 03/19/2025;
| Given I try to access basket data directly, when I do so, then I receive an error or restricted access message. | Pass | E.L.; 03/19/2025;
As a U-fund Manager, I want to manage the needs stored in the needs cupboard so that I can ensure accurate and up-to-date information. | Given I am logged in as a U-fund Manager, when I visit the needs cupboard, then I can see all the stored needs. | Pass | E.Z.W. 03/19/2025;
| Given I want to add a new need, when I enter the details and submit, then the need is saved to the cupboard. | Pass | E.Z.W. 03/19/2025;
| Given I want to update a need, when I modify its details and save, then the cupboard reflects the changes. | Pass | E.Z.W. 03/19/2025;
| Given I want to delete a need, when I confirm removal, **then **the need is no longer in the cupboard. | Pass | E.Z.W. 03/19/2025;
| Given I log out and log back in, when I visit the cupboard, then all modifications persist. | Pass | S.L.; 03/19/2025
As a Helper, I want to add or remove needs from my funding basket so that I can manage what I plan to fund. | Given I am viewing a need, when I click "Add to Basket," then the need is saved to my basket. | Pass | S.L.; 03/19/2025
| Given a need is already in my basket, when I click "Remove," then it is removed from my basket. | Pass | S.L.; 03/19/2025
As a Helper I want to check out and fund my selected needs so that I can complete my contribution | Given I have needs in my basket, when I proceed to checkout, then I will see a summary of what I am funding |  | not implemented yet
| Given I confirm the checkout, when I complete the process, then my basket is cleared and the needs are marked as funded |  | not implemented yet
| Given I log out and log back in, when I visit my basket, then I see an empty basket after a successful checkout |  | not implemented yet
As a user, I want to save my changes so that I don't have to restart every time I log back in | Given I change something as a user, when I log out then I expect my changes to be saved for when I log back in |  | not implemented yet